## Cover Sheet
Construction Bid Sheet
Project Name | River's Edge Foundation Repair
Location | 434 6th Ave, Raymond WA
Estimated Start Date | 2025-10-01 | Estimated Completion |  | 2025-12-01
| Ownewr Information |  | Contractor Information
Name | Joint Pacific County Housing Authority
Contact | Laura Jackson
Address | 820 11th Ave Longview, WA
Phone | 360.423.0140 ext 1050
Email | laura.jackson@hoswwa.org
Scope of Work: A Piles
The plan shows 62 piles with an A rating, the remediation for these piles, as recommended in the report, is as follows: In more moderate cases, the damaged pile may be treated in place to prevent additional deterioration. This treatment should include cutting away all deteriorated portions of the existing pile and treating the existing wood with a fungal growth inhibitor to prevent additional deterioration. Piles with more than 1.5” but less than 4" of deterioration at any face should have supplemental framing installed to replace the deteriorated sections of the pileas depicted in detail SK-2 included in the original bid documents . The supplemental framing should consist of pressure treated wood, not less than 3.5” thick (4x material), and should be securely attached to the existing pile material. For bidding purposes contractors should assume 30% of A rated piles have more than 1.5” of deterioration and will require remediation beyond painting and sealing
Scope of Work: B Piles
Seven (7) of the piles are given a B rating, the remediation for these piles, as recommended in the report, is as follows: Piles with more significant deterioration (more than 4” deep at any face), but where the rot does not extend below the existing grade, may be repaired by replacing the rotten pile cap with a new treated timber member of the same size, as shown in SK-3 detail included in the original bid documents. All of the cut ends of the new and existing piles should be treated with a rot inhibitor, and the joint between the two piles should be sealed with a silicone-based sealant to prevent moisture accumulation between the two segments of pile.
Scope of Work: C Piles
The 12, C rated pilings as called out on the plan should be remediated per the report: In locations where the deterioration at the pile extends to or below the existing grade, the soil around the pile will need to be excavated (no more than 30" below grade) in order to locate the extent of the rot and find sound bearing material in the pile. Then a new concrete cap can be poured around the top of the pile and extended up above grade as shown in SK-4 detail included in the original bid documents.
|  | Bid Total |  | 0
Signature |  |  |  | Date

## A Piles
Construction Bid Sheet
Project Name | River's Edge Foundation Repair
Cost Breakdown A Piles
Materials and Services not included:
Materials
Qty | Component |  | Rate | Cost
| Fungal Growth Inhibitor |  |  | 0
| Sealant |  |  | 0
| Pressure Treated 4x8 & 4x12 sections no longer than 12" |  |  | 0
| Simpson .22" x 10" SDWS Timber Screws (Min 8 per pile) |  |  | 0
|  |  | Subtotal | 0
Labor
Activity |  | Hours | Rate | Cost
0
0
0
0
0
|  |  | Subtotal | 0
Miscellaneous
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | Materials | 0
|  |  | Labor | 0
|  |  | Miscellaneous | 0
|  |  | Total | 0

## B Piles
Construction Bid Sheet
Project Name | River's Edge Foundation Repair
Cost Breakdown B Piles
Materials and Services not included:
Materials
Qty | Component |  | Rate | Cost
| Fungal Growth Inhibitor |  |  | 0
| Sealant |  |  | 0
| Simpson HST2 Straps |  |  | 0
| Full width Pile Section 24" Max |  |  | 0
| 5/8" Dia Bolts, Galvanized |  |  | 0
| MTS12 Twist Straps |  |  | 0
|  |  | Subtotal | 0
Labor
Activity |  | Hours | Rate | Cost
0
0
0
0
0
|  |  | Subtotal | 0
Miscellaneous
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | Materials | 0
|  |  | Labor | 0
|  |  | Miscellaneous | 0
|  |  | Total | 0

## C Piles
Construction Bid Sheet
Project Name | River's Edge Foundation Repair
Cost Breakdown C Piles
Materials and Services not included:
Materials
Qty | Component |  | Rate | Cost
| Fungal Growth Inhibitor |  |  | 0
| Sealant |  |  | 0
| Simpson HST2 Straps |  |  | 0
| PT 8X10X36 Post |  |  | 0
| 5/8" Dia Bolts, Galvanized |  |  | 0
| CB810 Post Base |  |  | 0
| Concrete Pile Cap |  |  | 0
| #4 Reinforcing Bars |  |  | 0
| #5 Reinforcing Bars |  |  | 0
|  |  | Subtotal | 0
Labor
Activity |  | Hours | Rate | Cost
0
0
0
0
0
|  |  | Subtotal | 0
Miscellaneous
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | Materials | 0
|  |  | Labor | 0
|  |  | Miscellaneous | 0
|  |  | Total | 0